## TOC
TABLE OF CONTENTS
No | Sheet | Last Updated
1 | Cover Page
2 | Defects Report
3 | Test Execution Summary Report

## CoverPage
‘Google Translator' application
Document Control information
Issue Date: | 20-04-2024
Issue Status: | Approved
Owner: | Dilma Vithanage
Author: | V1
Approver information
Document Revision History
Date | Version | Description | Revised by
Purpose
This document explains the various activities performed as part of Testing of ‘Google Translator’ application.
Application Overview
‘Google Translator’’ is a web based language tranlate application. Which allow to tranlate in to wide range of languagres via text, voice , imgers, document and webURL as inputs.
Testing Scope
a) In Scope
Translations via via text, voice , imgers, document and webURL as inputs.
b) Out of Scope
Performance Testing was not done for this application.

## Defects
Defect ID | Module | Defect Summary | Steps to reproduce | Severity | Priority | Status | Created by | Assigned to | Comments
BUG-001 |  | User doesn't notify when Clicks speak button by adding input is not in selected language | 1. Navigate to Text field 2. Add content which need to translate( in Sinhala) 3. Select language in the input field ad italian 5. Click on the speaker icon 6. Verify the output | Medium | low | Open | Dilma VIthanage | Dev
BUG-002 |  | Translator doesn't detect when user input is added in a different than the selected language | 1. Navigate to Text field 2. Add content with different language than selected one(Eg: select sinhala and add english text) 3. Verify the output | Medium | low | Open | Dilma VIthanage | Dev
[10 empty] | Critical | Open
[10 empty] | High | Closed
Medium
Low

## TestExecution
Functional Test Execution Summary | TC Count | %
Total Test cases Assigned | 33
In Scope | 33
Executed | 33 | 100%
Not Executed | 0 | 0%
Passed | 31 | 93.94%
Failed | 2 | 6.061%
Blocked | 0 | 0%
Out of Scope | 0 | 0%
Defects Priority and Status
Severity | Total
Critical | 0
High | 0
Medium | 2
Low | 0
Total | 2
Defects Severity and Status
Status | Critical | High | Medium | Low | Total
Closed | 0 | 0 | 0 | 0 | 0
Open | 0 | 0 | 0 | 2 | 0